## Post Proposal
Known Unknowns Program
Time
Date | In | Out | Hours | Cost | Details
2022-08-04 | 7:24 | 7:59 | 0.58333 | 43.75 | Worked on proposal changes
2022-08-05 | 6:48 | 8:16 | 1.4667 | 110 | Worked on proposal changes
2022-08-23 | 19:22 | 21:00 | 1.6333 | 122.5 | Added radio buttons for ICK expansion, and number for training trials correct to advance feature.

## Original
Known Unknowns Program
Time
Date | In | Out | Hours | Cost | Details
2021-10-05 | 7:33 | 9:25 | 1.8667 |  | Deliverable Schedule, Workspace Setup, Github pages deployment
2021-10-06 | 6:58 | 9:11 | 2.2167 |  | Added study form, form validation routing
2021-10-06 | 13:57 | 14:37 | 0.66667 |  | Improved form ui, and adding copy link with params
2021-10-07 | 5:38 | 9:36 | 3.9667 |  | Added study component, added config service, and param parsing.
2021-10-08 | 6:36 | 7:35 | 0.98333 |  | Worked on generating trigrams and randomization keys. Realized that we might need a dictionary.
2021-10-09 | 7:00 | 7:30 | 0.5 |  | Reorganized constants and functions, and created constants needed for randomized study conditions.
2021-10-10 | 10:08 | 12:52 | 2.7333 |  | Converted buttons to svg format, and created draft of button html.
2021-10-10 | 13:33 | 13:55 | 0.36667 |  | Worked on trial UI and randomization.
2021-10-10 | 14:40 | 18:49 | 4.15 |  | Worked on trial UI and randomization.
2021-10-10 | 19:46 | 21:30 | 1.7333 |  | Worked on trial UI and randomization.
2021-10-11 | 8:20 | 12:49 | 4.4833 |  | Addressed animation issues, and refactored various components to prepare for creating blocks.
2021-10-11 | 17:42 | 21:00 | 3.3 |  | Created network.
2021-10-12 | 20:32 | 23:41 | 3.15 |  | Fix scaling and add overlay service.
2021-10-13 | 22:00 | 23:59 | 1.9833 |  | Refactored network classes, fixed typing.
2021-10-14 | 0:00 | 1:01 | 1.0167 |  | Created forced choice phase.
2021-10-24 | 10:00 | 18:00 | 8 | 0 | Refactored application. Time isn’t billable.
2021-10-27 | 6:32 | 9:22 | 2.8333 |  | Modified forced choice phase according to conversation with patrick.
2021-10-28 | 5:28 | 10:17 | 4.8167 |  | Modified forced choice phase according to 2nd conversation with patrick.
2021-10-29 | 6:33 | 10:20 | 3.7833 |  | Modified forced choice phase according to 3rd conversation with patrick.
2021-10-30 | 6:46 | 10:18 | 3.5333 |  | Abstracted block class so that the previous block works as expected. Added comments to block code.
2021-10-31 | 7:20 | 12:53 | 5.55 |  | Refactored code to improve code quality.
2021-11-01 | 6:30 | 12:38 | 6.1333 | 0 | Create custom graph library. Time is not billable.
2021-11-02 | 6:24 | 9:56 | 3.5333 |  | Generated relational frame using graph.
2021-11-03 | 6:23 | 9:22 | 2.9833 |  | Replace networks with graph and added graph relationships for test and forced choice blocks. Tested changes.
2021-11-04 | 6:35 | 8:00 | 1.4167 |  | Replace networks with graph and added graph relationships for operant choice block. Tested changes.
2021-11-05 | 6:30 | 7:33 | 1.05 |  | Added sequential correct, block timeout, and correct counter for each
2021-11-06 | 7:30 | 9:45 | 2.25 |  | Added master critierion 1 and 2
2021-11-07 | 6:26 | 7:40 | 1.2333 |  | Fixed operant choice bugs related to timeout, retry, and looping through trials. Tested trial several times.
2021-11-09 | 6:28 | 7:34 | 1.1 |  | Worked on training networks block.
2021-11-10 | 6:44 | 9:25 | 2.6833 |  | Finished draft of training networks block.
2021-11-11 | 7:16 | 9:24 | 2.1333 |  | Added time out to training networks block, and missing time expired sound. Chained all blocks together and tested through entire chain twice.
2021-11-12 | 6:25 | 8:20 | 1.9167 |  | Worked on report service
2021-11-13 | 9:00 | 14:39 | 5.65 |  | General refactoring
2021-11-15 | 7:10 | 9:28 | 2.3 |  | Refactored application for apple products.
2021-11-15 | 18:00 | 18:41 | 0.68333 | 0 | Added progressive web application. Time is not billable.
2021-11-16 | 7:10 | 10:28 | 3.3 |  | Finished implementing
2021-11-17 | 7:50 | 9:42 | 1.8667 |  | Integrated emailJS, set up templates, accound, and domain whitelist.